## Sheet1
Bug ID | Title | Module | Steps | Expected Result | Actual Result | Severity | Priority | Status | Enivornment | Date | Reported by
Bug_01 | Missing required fields for checkout | Checkout | 1. Open checkout page 2. Enter First Name, Last Name, Postal Code 3. Leave Email, Phone, Address empty 4. Click Continue | System should require email, phone and address | Checkout continues without required contact or shipping details | High | High | New | Web - SauceDemo | 2026-01-28 | M. Salman
Bug_02 | Multiple session login without logout | Multiple account session switch issue | 1. Login with User A 2. After successful login, open login form again 3. Login with User B 4. System logs in User B without asking logout confirmation | Ask to logout User A before login User B OR Automatically invalidate old session OR Prevent login until session cleared | User B logs in without clearing previous session | Medium | Medium | New | Web - SauceDemo | 2026-01-28 | M. Salman
Bug_03 | Sorting dropdown not working properly | Product Listing / Sorting | 1. Open product listing page 2. Locate sorting control (A-Z / Z-A / Low to High / High to Low) 3. Click on the dropdown arrow icon 4. Notice that dropdown does NOT open 5. Now click on the text label | Dropdown should open on arrow or label click and allow sorting selection. | Dropdown does not open when clicking arrow; works only on label click. | Medium | Medium | New | Web - SauceDemo | 2026-01-28 | M. Salman
Bug_04 | Search overlay hides content + arrows not working | Search / UI Overlay / Dashboard | 1. Login to the dashboard 2. Click on the Search icon 3. Enter any keyword (e.g., “test”) 4. A full template/overlay appears showing Selenium and other items Hover the mouse over those items 5. The overlay hides the content immediately 6. Also click on the navigation arrows under the template 7. Notice that neither left nor right arrow works | Search overlay should remain visible when hovering Template content should not auto-hide Navigation arrows should switch items or sliders UI interaction should remain stable | Overlay hides automatically on hover Content flickers / disappears Navigation arrows do not work Search results UI is unstable | High | High | New | Web - SauceDemo | 2026-01-28 | M. Salman
Bug_05 | Product image not zooming or opening | Product Details / Image Viewer | 1. Open any product page 2. Click on the product image 3. Observe system behavior | Image should open in gallery mode OR Zoom mode OR New tab OR Lightbox/fullscreen view | Clicking image does nothing Image does not zoom Image does not open in viewer No maximize or minimize functionality | Medium | Medium | New | Web - SauceDemo | 2026-01-28 | M. Salman
Bug_06 | Checkout completes with empty cart | Cart / Checkout / Order Processing | 1.Do not add any item to cart 2.Click on Checkout 3.Enter First Name, Last Name, Postal Code 4.Click Continue 5.Click Finish | System should prevent checkout when cart is empty . Your cart is empty . Add items before checkout . No items found to process order | Checkout allowed with empty cart Order completed successfully No error message shown System processed empty order | High | High | New | Web - SauceDemo | 2026-01-28 | M. Salman